## KPI_2025
KPI | EmployeeID | EmployeeName | Weightage | Year | Q3Target | Q3Actual | Q3Achieved | OKR Link | Q4Target | Q4Actual | Q4Achieved | OKR Link | Title
Project Delivery | 2012 | Krishna | 58 | 2025 | More >85% alignment with Project delivery checklist | 0 closed (target 8) — under training/KT; PM Yes | Yes | Krishna_OKR_Checklist!A10 | More >85% alignment with Project delivery checklist | 7 closed (target 3) | Yes | Krishna_OKR_Checklist!A14 | TSE
Process Adherance | 2012 | Krishna | 12 | 2025 | More > 90% discipline to be followed for Process Checklist | Tickets in qtr=0; closed=0 — see Helpdesk_Discipline | Yes | Krishna_OKR_Checklist!A11 | More > 90% discipline to be followed for Process Checklist | Tickets in qtr=7; closed=7 — see Helpdesk_Discipline | Yes | Krishna_OKR_Checklist!A15 | TSE
External Bug Count, Ticket Reopen | 2012 | Krishna | 16 | 2025 | External bugs (Client reported) to be <= 4 of total tickets delivered in quarter | Closed=0; defect-themes=0; rework-proxy=0 | Yes | Krishna_OKR_Checklist!A12 | External bugs (Client reported) to be <= 4 of total tickets delivered in quarter | Closed=7; defect-themes=0; rework-proxy=0 | Yes | Krishna_OKR_Checklist!A16 | TSE
Self Learning | 2012 | Krishna | 14 | 2025 | 1 POC submission- Microsoft Login Accelerator / Helpdesk KT | POC: Microsoft Authentication Accelerator — see Learning_Evidence (problem/AC/tech). Source: PMS/Krishna/Krishnaraj_POC_25-26.xlsx | Yes | Krishna_OKR_Checklist!A13 | 1 POC submission- Microsoft Login Accelerator / Helpdesk KT | POC: Resilient API Communication using Polly — see Learning_Evidence (problem/AC/tech). Source: PMS/Krishna/Krishnaraj_POC_25-26.xlsx | Yes | Krishna_OKR_Checklist!A17 | TSE
Quarterly Score |  |  | 100 | 2025 |  | 100 / 100 weightage points (under training — PM Yes) | 100 | Krishna_OKR_Checklist!A1 |  | 100 / 100 weightage points | 100 | Krishna_OKR_Checklist!A1

## KPI_2026
KPI | EmployeeID | EmployeeName | Weightage | Year | Q1Target | Q1Actual | Q1Achieved | OKR Link | Q2Target | Q2Actual | Q2Achieved | OKR Link | Q3Target | Q3Actual | Q3Achieved | OKR Link | Q4Target | Q4Actual | Q4Achieved | OKR Link
Execution | 2012 | Krishna | 30 | 2026 | ≥8 tickets/tasks to Production (~2.5/month); QA handoffs within sprint dates; ≤2 slippages; deployment evidence in Helpdesk Plus. | 8 closed (target 8) | Yes | Krishna_OKR_Checklist!A2 | ≥12 tickets/tasks to Production (~4/month); estimation within ±10%; on-time handoff to QA; proactive delay risks. | 19 closed (target 12) | Yes | Krishna_OKR_Checklist!A6 | ≥14 tickets/tasks to Production (~4–5/month); ≤2 slippages/quarter; blockers cleared within 72h. |  |  | Krishna_OKR_Checklist!A1 | ≥16 tickets/tasks to Production (~5+/month); zero uncommunicated delays; release documentation complete. |  |  | Krishna_OKR_Checklist!A1
Quality | 2012 | Krishna | 50 | 2026 | Quality Score card >=80% — >95% Helpdesk Plus process adherence; ≤20 rework tickets; zero critical/major escapes; PR template 100%; test evidence on complex items. | Closed=8; defect-themes=2; rework-proxy=0 | Yes | Krishna_OKR_Checklist!A3 | Quality Score card >=80% — >95% process adherence; ≤15 rework tickets; peer review clean on deltas; one quality improvement logged. | Closed=19; defect-themes=2; rework-proxy=0 | Yes | Krishna_OKR_Checklist!A7 | Quality Score card >=85% — >95% process adherence; ≤10 rework tickets; 1 concrete MDM/EPC quality improvement; critical fixes per SLA. |  |  | Krishna_OKR_Checklist!A1 | Quality Score card >=85% — ≤5 rework tickets; zero critical escapes; Q1 vs Q4 rework trend documented for appraisal; annual process audit ready. |  |  | Krishna_OKR_Checklist!A1
Learning & Development | 2012 | Krishna | 20 | 2026 | AI-assisted development (Cursor/ChatGPT) and async programming fundamentals. POC: AI-powered PR/code reviewer assistant. | POC: AI-assisted development (Cursor/ChatGPT) and async programming fundamentals. POC: AI-power — see Learning_Evidence. Repo: https://bitbucket.org/msnalashaa/performance-learning-development/src/main/ | Yes | Krishna_OKR_Checklist!A5 | .NET API fundamentals & REST patterns. POC: Build one .NET API module with Swagger documentation and unit/integration tests. | POC: .NET API fundamentals & REST patterns. POC: Build one .NET API module with Swagger documen — see Learning_Evidence. Repo: https://bitbucket.org/msnalashaa/performance-learning-development/src/main/ | Yes | Krishna_OKR_Checklist!A9 | SQL query optimization & stored procedures. POC: Optimize one slow query with verified before/after metrics. |  |  | Krishna_OKR_Checklist!A1 | Integrated capstone — extend AI PR/code reviewer with .NET API backend and SQL-backed review metrics; annual upskilling portfolio. |  |  | Krishna_OKR_Checklist!A1
Quarterly Score |  | Krishna | 100 |  |  | 100 / 100 weightage points | 100 | Krishna_OKR_Checklist!A1 |  | 100 / 100 weightage points | 100 | Krishna_OKR_Checklist!A1 |  |  |  | Krishna_OKR_Checklist!A1 |  |  |  | Krishna_OKR_Checklist!A1

## OKR_Summary
OKR Weightage Summary — governed by Krishna_OKR_Checklist (Met?) + Tickets_Master for delivery
Appraisal scope: 2025 Q3–Q4 + 2026 Q1–Q2. Q3-2025 = training/KT (PM Yes).
KPI / Met? | Q3-2025 | Q4-2025 | Q1-2026 | Q2-2026 | Grand Total
Execution
Yes |  |  | 5 | 5 | 10
No
Quality
Yes |  |  | 10 | 10 | 20
No
Learning & Development
Yes |  |  | 5 | 5 | 10
No
Project Delivery
Yes | 58 | 58 |  |  | 116
No
Process Adherance
Yes | 12 | 12 |  |  | 24
No
External Bug Count, Ticket Reopen
Yes | 16 | 16 |  |  | 32
No
Self Learning
Yes | 14 | 14 |  |  | 28
No
Grand Total | 100 | 100 | 20 | 20 | 240
Training / KT Note
Q3-2025 note (PM): Krishna was under training during Q3-2025. He is taking KT (knowledge transfer) and working on small parts of the tickets. Q3-2025 Achieved marked Yes accordingly (master has 0 tickets that quarter).

## OKR_Checklist_Summary
OKR Checklist Summary — governed by Krishna_OKR_Checklist (Met? weightages)
Built from hub. No column empty when all OKRs Met?=Yes (incl. Q3-2025 training).
Quarter / KPI | No | Yes | Grand Total
Q3-2025 |  | 100 | 100
Project Delivery |  | 58 | 58
Process Adherance |  | 12 | 12
External Bug Count, Ticket Reopen |  | 16 | 16
Self Learning |  | 14 | 14
Q4-2025 |  | 100 | 100
Project Delivery |  | 58 | 58
Process Adherance |  | 12 | 12
External Bug Count, Ticket Reopen |  | 16 | 16
Self Learning |  | 14 | 14
Q1-2026 |  | 20 | 20
Execution |  | 5 | 5
Quality |  | 10 | 10
Learning & Development |  | 5 | 5
Q2-2026 |  | 20 | 20
Execution |  | 5 | 5
Quality |  | 10 | 10
Learning & Development |  | 5 | 5
Grand Total |  | 240 | 240
Training / KT Note
Q3-2025 note (PM): Krishna was under training during Q3-2025. He is taking KT (knowledge transfer) and working on small parts of the tickets. Q3-2025 Achieved marked Yes accordingly (master has 0 tickets that quarter).

## Krishna_OKR_Checklist
Employee Name | Quarter | KPI Affected | OKR Met? | Weightage | Artifacts to OKR | Other Links | OKRs | Deliverable Expected | Evidence Note
Krishna | Q1-2026 | Execution | Yes | 5 | Ticket_Velocity!A1 | Q1-2026_Tickets!A1 | 1. Achieve ≥8 Production deployments with traceable Helpdesk Plus releases 2. Maintain ≤2 task slippages with documented PM/stakeholder email 3. QA handoff within 2 business days of dev-complete on committed items 4. Obtain PM sign-off on Q1 delivery milestone | 1. Project Delivery Checklist completed (≥70% compliance) 2. Helpdesk Plus tickets with version/release + deployment notes 3. Slippage log with email evidence (if any) 4. Q1 Delivery Report + PM sign-off | Master Q1-2026: total=10 closed=8 open=2 (target 8; Yes if >=8 or >=5)
Krishna | Q1-2026 | Quality | Yes | 5 | Helpdesk_Discipline!A1 | Q1-2026_Tickets!A1 | 1. Achieve ≥95% Process Adherence Checklist score (≥19/20 sampled tickets) 2. Daily Helpdesk Plus logging and worklog discipline on assigned tasks 3. 100% PR template usage on all submissions 4. Zero uncommunicated ticket stalls or update misses | 1. Completed Process Adherence Checklist with score 2. Worklog audit sample (20 Helpdesk Plus tickets) 3. PR template compliance evidence 4. Q1 Process Report | Evidence-based; Closed=8
Krishna | Q1-2026 | Quality | Yes | 5 | CodeChange_Summary!A1 | Q1-2026_Tickets!A1 | 1. Keep rework tickets ≤20 (reopened or QA-returned on owned work) 2. Zero critical/major escapes to Production in owned scope 3. Avg PR review score ≥4/5 per team peer-review rubric 4. Attach test evidence on all complex items | 1. Helpdesk Plus rework ticket count report (baseline ≤20) 2. Peer code review sign-off on all changed code 3. RCA document on any prod escape 4. Q1 Quality Report | Evidence-based; Closed=8
Krishna | Q1-2026 | Learning & Development | Yes | 5 | Learning_Evidence!A1 | https://bitbucket.org/msnalashaa/performance-learning-development/src/main/ | POC: AI-assisted development (Cursor/ChatGPT) and async programming fundamentals. POC: AI-powered PR/code reviewer assistant. Problem: Manual code reviews can be time-consuming and may miss common issues such as bugs, null-reference risks, security concerns, performance problems, and async/await issues. The POC explores how AI can assist developers by automatically analyzing Pull Request code changes and providi… AC: • Accept a Pull Request-style code diff as input. • Send the code changes to an AI model for analysis. • Identify potential bugs, security, performance, async, and code-quality issues. • Return structured review findings with severity, description, and suggested fixes. • Use asyn… Stack: C# / .NET 8, Visual Studio 2022, Google Gemini API, Google.GenAI SDK, async/await, System.Text.Json | • Gained practical experience integrating an LLM API into a .NET application. • Applied async/await and asynchronous I/O for file processing and external API communication. • Learned prompt engineering for structured AI responses. • Used AI-assisted development to accelerate coding, debugging, refactoring, and documentation. • Applied basic separation of concerns through service interfaces, AI service, prompts, and models. • Established a foundation for future GitHub/GitLab PR automation. | See Learning_Evidence Q1-2026 (problem/AC/tech). Source: PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Krishna | Q2-2026 | Execution | Yes | 5 | Ticket_Velocity!A1 | Q2-2026_Tickets!A1 | 1. Achieve ≥12 Production deployments with linked release references 2. Estimation within ±2 days vs sprint commitment on owned items 3. On-time QA handoff; proactive delay risks raised to PM within 24h 4. Obtain PM sign-off on Q2 throughput milestone | 1. Project Delivery Checklist completed (≥75% compliance) 2. Sprint outcomes vs estimate tracking sheet 3. Helpdesk Plus tickets with release references on all closed items 4. Q2 Delivery Milestone Report + PM sign-off | Master Q2-2026: total=20 closed=19 open=1 (target 12; Yes if >=12 or >=8)
Krishna | Q2-2026 | Quality | Yes | 5 | Helpdesk_Discipline!A1 | Q2-2026_Tickets!A1 | 1. Maintain ≥95% Process Adherence Checklist score 2. MoMs for all key decisions and material client/internal discussions 3. Stakeholder responsiveness within agreed SLAs 4. Worklogs aligned to Helpdesk Plus tasks with no silent slippages | 1. Completed Process Adherence Checklist with score 2. MoMs archived in wiki/email 3. Escalation email trail where applicable 4. Q2 Process Report + PM/RM sampling sign-off | Evidence-based; Closed=19
Krishna | Q2-2026 | Quality | Yes | 5 | CodeChange_Summary!A1 | Q2-2026_Tickets!A1 | 1. Keep rework tickets ≤15 (reopened or QA-returned on owned work) 2. Zero critical/major escapes to Production in owned scope 3. Peer code review clean on all code deltas 4. Log and track one quality improvement with owner assigned | 1. Rework ticket count trend vs Q1 (target ≤15) 2. Quality improvement ticket + assigned owner 3. QA collaboration evidence on improvement 4. Q2 Quality Report | Evidence-based; Closed=19
Krishna | Q2-2026 | Learning & Development | Yes | 5 | Learning_Evidence!A1 | https://bitbucket.org/msnalashaa/performance-learning-development/src/main/ | POC: .NET API fundamentals & REST patterns. POC: Build one .NET API module with Swagger documentation and unit/integration tests. Problem: Demonstrate the design and implementation of a RESTful .NET API module using standard API patterns, CRUD operations, validation, documentation, and automated testing. AC: Build a functional .NET API module with RESTful CRUD endpoints; provide Swagger/OpenAPI documentation; implement request validation and appropriate HTTP status codes; add unit and integration tests with all tests passing. Stack: .NET 8, ASP.NET Core Web API, C#, Swagger/Swashbuckle, xUnit, WebApplicationFactory, In-memory Repository | Built and tested a Product REST API with GET, POST, PUT, and DELETE endpoints using Controller-Service-Repository architecture. Added DTO validation, Swagger documentation, and automated testing with 8 unit tests and 5 integration tests, achieving 13/13 passing tests. Gained practical understanding of REST API design, HTTP methods/status codes, dependency injection, API validation, Swagger/OpenAPI, unit testing, and integration testing using WebApplicationFactory. | See Learning_Evidence Q2-2026 (problem/AC/tech). Source: PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Krishna | Q3-2025 | Project Delivery | Yes | 58 | Ticket_Velocity!A1 |  | Project Delivery — appraisal scope Q3-2025 | Per KPI_2025 target | Under training / KT — 0 master tickets; PM Yes
Krishna | Q3-2025 | Process Adherance | Yes | 12 | Helpdesk_Discipline!A1 |  | Process Adherance — appraisal scope Q3-2025 | Per KPI_2025 target | Evidence-based from KPI/tickets; Actual=Tickets in qtr=0; closed=0 — see Helpdesk_Discipline
Krishna | Q3-2025 | External Bug Count, Ticket Reopen | Yes | 16 | Customer_Defect_Themes!A1 |  | External Bug Count, Ticket Reopen — appraisal scope Q3-2025 | Per KPI_2025 target | Evidence-based from KPI/tickets; Actual=Closed=0; defect-themes=0; rework-proxy=0
Krishna | Q3-2025 | Self Learning | Yes | 14 | Learning_Evidence!A1 | PMS/Krishna/Krishnaraj_POC_25-26.xlsx | POC: Microsoft Authentication Accelerator Problem: Develop a reusable authentication library to simplify Microsoft OAuth 2.0 token acquisition for .NET applications and reduce repeated authentication boilerplate. The accelerator should centralize configuration, token acquisition, error handling, logging, silent token acquisition,… AC: 1) Reusable .NET class library abstracts MSAL OAuth 2.0 token acquisition. 2) Centralized configuration, error handling, logging, silent token acquisition, Forgot Password URL. 3) Simple interface/builder for consumer apps; DI + appsettings-driven config. 4) Validated via console… Stack: C#, .NET 8 / .NET class library, MSAL.NET, Microsoft.Extensions.Configuration, Microsoft.Extensions.DependencyInjection, Microsoft.Extensions.Logging, Microsoft Identity Platform, OAuth 2.0, appsettings.json | Built a reusable authentication accelerator that abstracts MSAL token-acquisition complexity behind a simple interface and builder. Implemented centralized logging and standardized authentication errors, while allowing consumer applications to handle interactive login when required. Validated the library through a console consumer application and successfully acquired an access token using configuration-driven authentication. Learned how MSAL token flows, token caching/silent acquisition, depend | See Learning_Evidence Q3-2025 (problem/AC/tech). Source: PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Krishna | Q4-2025 | Project Delivery | Yes | 58 | Ticket_Velocity!A1 | Q4-2025_Tickets!A1 | Project Delivery — appraisal scope Q4-2025 | Per KPI_2025 target | Master Q4-2025: total=7 closed=7 open=0 (target 3; Yes if >=3 or >=2)
Krishna | Q4-2025 | Process Adherance | Yes | 12 | Helpdesk_Discipline!A1 | Q4-2025_Tickets!A1 | Process Adherance — appraisal scope Q4-2025 | Per KPI_2025 target | Evidence-based from KPI/tickets; Actual=Tickets in qtr=7; closed=7 — see Helpdesk_Discipline
Krishna | Q4-2025 | External Bug Count, Ticket Reopen | Yes | 16 | Customer_Defect_Themes!A1 | Q4-2025_Tickets!A1 | External Bug Count, Ticket Reopen — appraisal scope Q4-2025 | Per KPI_2025 target | Evidence-based from KPI/tickets; Actual=Closed=7; defect-themes=0; rework-proxy=0
Krishna | Q4-2025 | Self Learning | Yes | 14 | Learning_Evidence!A1 | PMS/Krishna/Krishnaraj_POC_25-26.xlsx | POC: Resilient API Communication using Polly Problem: APIs that depend on downstream services can be affected by temporary failures, slow responses, or repeated service failures. The POC was created to understand and demonstrate how API resilience patterns can handle these situations in a controlled manner. AC: Demonstrate successful downstream communication; automatically retry transient failures; terminate slow requests using timeout handling; open the circuit after repeated failures; return meaningful 502, 503, and 504 responses; document the implementation and validation scenarios. Stack: .NET 8, ASP.NET Core Web API, C#, Polly, Microsoft.Extensions.Http.Resilience, HttpClient, Swagger/OpenAPI, Dependency Injection, Async/Await | Gained practical understanding of API resilience, retry and backoff strategies, per-attempt vs overall timeout, circuit breaker states, and handling downstream failures without directly exposing infrastructure exceptions to API consumers. | See Learning_Evidence Q4-2025 (problem/AC/tech). Source: PMS/Krishna/Krishnaraj_POC_25-26.xlsx

## Actual_vs_Achieved_Scorecard
Krishna_OKR_Checklist!A1
Krishna — Actual vs Achieved Scorecard (by Quarter)
Appraisal scope: 2025 Q3–Q4 + 2026 Q1–Q2. Learning POCs from PMS/Krishna/Krishnaraj_POC_25-26.xlsx (problem/AC/tech on Learning_Evidence). Repo: https://bitbucket.org/msnalashaa/performance-learning-development/src/main/.
Quarter | KPI Area | Metric | Target | Actual | Yes | Weightage (KPI) | Evidence Sheet | Source KPI Target (short) | Validation Notes
Q3-2025 | Project Delivery | Closed / Resolved tickets | 8 | 0 | Yes | 58 | Ticket_Velocity!A1 |  | Under training / KT — PM Yes (0 master tickets)
Q3-2025 | Process Adherance | Process checklist | >=90% | Tickets=0; closed=0 | Yes | 12 | Helpdesk_Discipline!A1 |  | Q score so far context: 0/100
Q3-2025 | External Bug Count, Ticket Reopen | Defect themes + rework | Themes<=4 | Themes=0; Rework=0 | Yes | 16 | Rework_Reopen_Proxy!A1 |  | Q score so far context: 0/100
Q3-2025 | Self Learning | Microsoft Authentication Accelerator | Problem + AC + Tech stack (see Learning_Evidence) | C#, .NET 8 / .NET class library, MSAL.NET, Microsoft.Extensions.Configuration, Microsoft.Extensions.DependencyInjection, | Yes | 14 | Learning_Evidence!A1 |  | From PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Q3-2025 | QUARTER SCORE | Sum of weightage Achieved=Yes | 100 | 100 | 100 | 100 | KPI_2025 |  | Score for send-out
Q4-2025 | Project Delivery | Closed / Resolved tickets | 3 | 7 | Yes | 58 | Ticket_Velocity!A1 |  | Q score so far context: 86/100
Q4-2025 | Process Adherance | Process checklist | >=90% | Tickets=7; closed=7 | Yes | 12 | Helpdesk_Discipline!A1 |  | Q score so far context: 86/100
Q4-2025 | External Bug Count, Ticket Reopen | Defect themes + rework | Themes<=4 | Themes=0; Rework=0 | Yes | 16 | Rework_Reopen_Proxy!A1 |  | Q score so far context: 86/100
Q4-2025 | Self Learning | Resilient API Communication using Polly | Problem + AC + Tech stack (see Learning_Evidence) | .NET 8, ASP.NET Core Web API, C#, Polly, Microsoft.Extensions.Http.Resilience, HttpClient, Swagger/OpenAPI, Dependency I | Yes | 14 | Learning_Evidence!A1 |  | From PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Q4-2025 | QUARTER SCORE | Sum of weightage Achieved=Yes | 100 | 100 | 100 | 100 | KPI_2025 |  | Score for send-out
Q1-2026 | Execution | Closed / Resolved tickets | 8 | 8 | Yes | 30 | Ticket_Velocity!A1 |  | Q score so far context: 70/100
Q1-2026 | Quality | Quality proxies (defect themes / rework) | Themes<=4; Rework<=20% | Themes=2; Rework=0; CodeSP=9 | Yes | 50 | Customer_Defect_Themes!A1 |  | Q score so far context: 70/100
Q1-2026 | Learning & Development | AI-assisted development (Cursor/ChatGPT) and async programming fundamentals. POC | Problem + AC + Tech stack (see Learning_Evidence) | C# / .NET 8, Visual Studio 2022, Google Gemini API, Google.GenAI SDK, async/await, System.Text.Json | Yes | 20 | Learning_Evidence!A1 |  | From PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Q1-2026 | QUARTER SCORE | Sum of weightage Achieved=Yes | 100 | 100 | 100 | 100 | KPI_2026 |  | Score for send-out
Q2-2026 | Execution | Closed / Resolved tickets | 12 | 19 | Yes | 30 | Ticket_Velocity!A1 |  | Q score so far context: 100/100
Q2-2026 | Quality | Quality proxies (defect themes / rework) | Themes<=4; Rework<=20% | Themes=2; Rework=0; CodeSP=21 | Yes | 50 | Customer_Defect_Themes!A1 |  | Q score so far context: 100/100
Q2-2026 | Learning & Development | .NET API fundamentals & REST patterns. POC: Build one .NET API module with Swagg | Problem + AC + Tech stack (see Learning_Evidence) | .NET 8, ASP.NET Core Web API, C#, Swagger/Swashbuckle, xUnit, WebApplicationFactory, In-memory Repository | Yes | 20 | Learning_Evidence!A1 |  | From PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Q2-2026 | QUARTER SCORE | Sum of weightage Achieved=Yes | 100 | 100 | 100 | 100 | KPI_2026 |  | Score for send-out
VALIDATION — Ticket totals vs Tickets_Master_Krishna (source of truth)
Scope | Total tickets | Closed | Open | Code Change | SP Change | Code Lines
All master | 40 | 37 | 3 | 25 | 23 | 1631
Appraisal quarters only | 37 | 34 | 3 | 22 | 23 | 1475
Per-quarter (must match Ticket_Velocity)
Quarter | Total | Closed | Open | Matches Velocity
Q3-2025 | 0 | 0 | 0 | Yes — from master
Q4-2025 | 7 | 7 | 0 | Yes — from master
Q1-2026 | 10 | 8 | 2 | Yes — from master
Q2-2026 | 20 | 19 | 1 | Yes — from master
Q3-2026 | 3 | 3 | 0 | Yes — from master

## Learning_Evidence
Krishna_OKR_Checklist!A1 | Krishna_OKR_Checklist!A1
Learning_Evidence — Self Learning / L&D POCs (quarter by quarter)
Appraisal scope: 2025 Q3–Q4 + 2026 Q1–Q2. POC details from PMS/Krishna/Krishnaraj_POC_25-26.xlsx. Repo (where applicable): https://bitbucket.org/msnalashaa/performance-learning-development/src/main/. Other quarters out of scope.
Quarter | KPI | POC / Focus Area | Problem Statement | Acceptance Criteria | Tech Stack | Evidence Link / Path | Achieved/Not Achieved | Primary Deliverable / Outcome | Comments
Q3-2025 | Self Learning | Microsoft Authentication Accelerator | Develop a reusable authentication library to simplify Microsoft OAuth 2.0 token acquisition for .NET applications and reduce repeated authentication boilerplate. The accelerator should centralize configuration, token acquisition, error handling, logging, silent token acquisition, and Forgot Password URL generation. | 1) Reusable .NET class library abstracts MSAL OAuth 2.0 token acquisition. 2) Centralized configuration, error handling, logging, silent token acquisition, Forgot Password URL. 3) Simple interface/builder for consumer apps; DI + appsettings-driven config. 4) Validated via console consumer — successfully acquire access token. 5) Demo / learning note for Q3 Self Learning KPI. | C#, .NET 8 / .NET class library, MSAL.NET, Microsoft.Extensions.Configuration, Microsoft.Extensions.DependencyInjection, Microsoft.Extensions.Logging, Microsoft Identity Platform, OAuth 2.0, appsettings.json | PMS/Krishna/Krishnaraj_POC_25-26.xlsx | Yes | Built a reusable authentication accelerator that abstracts MSAL token-acquisition complexity behind a simple interface and builder. Implemented centralized logging and standardized authentication errors, while allowing consumer applications to handle interactive login when required. Validated the library through a console consumer application and successfully acquired an access token using configuration-driven authentication. Learned how MSAL token flows, token caching/silent acquisition, dependency injection, structured logging, configuration binding, and reusable .NET library design can be combined into a plug-and-play authentication component. | From PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Q4-2025 | Self Learning | Resilient API Communication using Polly | APIs that depend on downstream services can be affected by temporary failures, slow responses, or repeated service failures. The POC was created to understand and demonstrate how API resilience patterns can handle these situations in a controlled manner. | Demonstrate successful downstream communication; automatically retry transient failures; terminate slow requests using timeout handling; open the circuit after repeated failures; return meaningful 502, 503, and 504 responses; document the implementation and validation scenarios. | .NET 8, ASP.NET Core Web API, C#, Polly, Microsoft.Extensions.Http.Resilience, HttpClient, Swagger/OpenAPI, Dependency Injection, Async/Await | PMS/Krishna/Krishnaraj_POC_25-26.xlsx | Yes | Gained practical understanding of API resilience, retry and backoff strategies, per-attempt vs overall timeout, circuit breaker states, and handling downstream failures without directly exposing infrastructure exceptions to API consumers. | From PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Q1-2026 | Learning & Development | AI-assisted development (Cursor/ChatGPT) and async programming fundamentals. POC: AI-powered PR/code reviewer assistant. | Manual code reviews can be time-consuming and may miss common issues such as bugs, null-reference risks, security concerns, performance problems, and async/await issues. The POC explores how AI can assist developers by automatically analyzing Pull Request code changes and providing structured review feedback. | • Accept a Pull Request-style code diff as input. • Send the code changes to an AI model for analysis. • Identify potential bugs, security, performance, async, and code-quality issues. • Return structured review findings with severity, description, and suggested fixes. • Use asynchronous programming for file and AI API operations. • Demonstrate AI-assisted development using ChatGPT/Cursor. | C# / .NET 8, Visual Studio 2022, Google Gemini API, Google.GenAI SDK, async/await, System.Text.Json | https://bitbucket.org/msnalashaa/performance-learning-development/src/main/ | Yes | • Gained practical experience integrating an LLM API into a .NET application. • Applied async/await and asynchronous I/O for file processing and external API communication. • Learned prompt engineering for structured AI responses. • Used AI-assisted development to accelerate coding, debugging, refactoring, and documentation. • Applied basic separation of concerns through service interfaces, AI service, prompts, and models. • Established a foundation for future GitHub/GitLab PR automation. | From PMS/Krishna/Krishnaraj_POC_25-26.xlsx
Q2-2026 | Learning & Development | .NET API fundamentals & REST patterns. POC: Build one .NET API module with Swagger documentation and unit/integration tests. | Demonstrate the design and implementation of a RESTful .NET API module using standard API patterns, CRUD operations, validation, documentation, and automated testing. | Build a functional .NET API module with RESTful CRUD endpoints; provide Swagger/OpenAPI documentation; implement request validation and appropriate HTTP status codes; add unit and integration tests with all tests passing. | .NET 8, ASP.NET Core Web API, C#, Swagger/Swashbuckle, xUnit, WebApplicationFactory, In-memory Repository | https://bitbucket.org/msnalashaa/performance-learning-development/src/main/ | Yes | Built and tested a Product REST API with GET, POST, PUT, and DELETE endpoints using Controller-Service-Repository architecture. Added DTO validation, Swagger documentation, and automated testing with 8 unit tests and 5 integration tests, achieving 13/13 passing tests. Gained practical understanding of REST API design, HTTP methods/status codes, dependency injection, API validation, Swagger/OpenAPI, unit testing, and integration testing using WebApplicationFactory. | From PMS/Krishna/Krishnaraj_POC_25-26.xlsx

## Ticket_Velocity
Krishna_OKR_Checklist!A1
Ticket_Velocity — governed by Tickets_Master_Krishna
Counts from master Quarter (Closure Date → Month → Assign). Targets: Q3-2025=8 (training/0 tickets → PM Yes), Q4-2025=3, Q1-2026=8, Q2-2026=12. Yes if closed >= target OR >= 70% of target.
Quarter | Total Tickets | Closed/Resolved | Open | Target | Yes/No | Comments | Source
Q3-2025 | 0 | 0 | 0 | 8 | Yes | Under training / KT — 0 tickets in master; PM Yes | Tickets_Master_Krishna
Q4-2025 | 7 | 7 | 0 | 3 | Yes | Met target (7/3) | Tickets_Master_Krishna
Q1-2026 | 10 | 8 | 2 | 8 | Yes | Met target (8/8) | Tickets_Master_Krishna
Q2-2026 | 20 | 19 | 1 | 12 | Yes | Met target (19/12) | Tickets_Master_Krishna
Q3-2026 | 3 | 3 | 0 | — | — | Outside appraisal scope (master completeness) | Tickets_Master_Krishna
MASTER TOTALS
Scope | Total | Closed | Open | Code Change | SP Change | Code Lines | SQL Lines
All master tickets | 40 | 37 | 3 | 25 | 23 | 1631 | 628
Appraisal only (Q3-2025..Q2-2026) | 37 | 34 | 3 | 22 | 23 | 1475 | 628

## Ticket_Spillover
Krishna_OKR_Checklist!A1 | Krishna_OKR_Checklist!A1
Ticket_Spillover (open Helpdesk tickets as spill proxy)
Open tickets (InProgress / OnHold / In-UAT / Approver) as spill proxy — no Jira sprint spill field.
Quarter | Total | Open (spill) | Spill % | Achieved/Not Achieved | Open Ticket Nos. | Comments
Q1-2026 | 10 | 2 | 20 | Yes | 27665, 32233 | Achieved if open<=2 or spill%<=20
Q2-2026 | 20 | 1 | 5 | Yes | 35275 | Achieved if open<=2 or spill%<=20
Q4-2025 | 7 | 0 | 0 | Yes | - | Achieved if open<=2 or spill%<=20

## FirstCut_Quality
Krishna_OKR_Checklist!A1 | Krishna_OKR_Checklist!A1
FirstCut_Quality (Helpdesk Code/SP Change quality proxy)
No Jira first-cut QA export. Proxy = Code/SP Change tickets closed with line counts (reviewable change).
Quarter | Code/SP Tickets | Closed Code/SP | Code Lines | SQL Lines | Achieved/Not Achieved | Comments
Q1-2026 | 10 | 8 | 388 | 182 | Yes | Quality Achieved — proxy; attach Azure PR screenshots if available
Q2-2026 | 20 | 19 | 835 | 318 | Yes | Quality Achieved — proxy; attach Azure PR screenshots if available
Q4-2025 | 7 | 7 | 252 | 128 | Yes | Quality Achieved — proxy; attach Azure PR screenshots if available

## CodeChange_Summary
Krishna_OKR_Checklist!A1 | Krishna_OKR_Checklist!A1
CodeChange_Summary — Azure DevOps / Bitbucket PR PROXY
PR rejection % cannot be pulled (no API permission). This sheet uses Helpdesk Code Change / SP Change + line counts as the auditable change evidence.
Quarter | Code Change Tickets | SP Change Tickets | Code Lines | SQL Lines | Achieved/Not Achieved | Comments
Q1-2026 | 5 | 7 | 388 | 182 | Yes | Quality Achieved — Link Other Links → CodeChange_Tickets for row-level list
Q2-2026 | 13 | 12 | 835 | 318 | Yes | Quality Achieved — Link Other Links → CodeChange_Tickets for row-level list
Q4-2025 | 4 | 4 | 252 | 128 | Yes | Quality Achieved — Link Other Links → CodeChange_Tickets for row-level list

## CodeChange_Tickets
Krishna_OKR_Checklist!A1 | Krishna_OKR_Checklist!A1
CodeChange_Tickets (row-level Code/SP Change list; paste Azure PR URL when available)
Paste Azure DevOps PR URL in column Azure_PR_URL when available (manual — no API).
Ticket No. | Description | Status | Quarter | Code Change | SP Change | Code Lines | SQL Lines | Assign Date | Closure Date | Azure_PR_URL (manual)
15635 | Mass Upload Needed for PRAC | Closed | Q1-2026 |  | yes |  | 44 | 2026-02-12 | 2026-03-13
16796 | Missing steering gear serial number | Closed | Q1-2026 | yes |  | 94 |  | 2026-02-03 | 2026-03-11
27665 | MDM - PRAC Overview (Add Structure Screen) | InProgress | Q1-2026 |  | yes |  | 22 | 2026-02-19
29717 | Supersessions not showing in EPC | Closed | Q1-2026 | yes | yes | 37 | 27 | 2025-12-07 | 2026-01-09
32233 | MDM - Division not updating | In Progress | Q1-2026 | yes | yes | 63 | 15 | 2025-12-27
32754 | Vin's not showing up in EPC | Closed | Q1-2026 |  | yes |  | 21 | 2025-12-22 | 2026-01-27
32836 | Vin's not showing up in EPC | Closed | Q1-2026 |  | yes |  | 17 | 2026-02-24 | 2026-03-19
33376 | EPC Enhancement 2 - VMRS Data in Part Search Table | Closed | Q1-2026 | yes | yes | 94 | 36 | 2025-12-06 | 2026-01-13
33439 | Volvo built Autocar VINs missing (194*** & 195***) | Closed | Q1-2026 | yes |  | 100 |  | 2025-12-27 | 2026-01-10
35062 | EPC - Module map links are broke | Closed | Q1-2026 | yes |  | 45 |  | 2026-02-11 | 2026-03-25
32776 | Vin's not showing up in EPC | Closed | Q2-2026 |  | yes |  | 19 | 2026-05-20 | 2026-06-10
33585 | EPC - A2390062-001 wrong 3D image in EPC | Closed | Q2-2026 | yes |  | 60 |  | 2026-04-07 | 2026-05-07
35023 | MDM - Updated Classification of Attached Parts List | Closed | Q2-2026 |  | yes |  | 25 | 2026-04-05 | 2026-05-13
35275 | MDM/EPC - Verify that back flush is working correct | In Progress | Q2-2026 | yes | yes | 58 | 20 | 2026-04-11
35340 | Vin. 227848 not showing up in EPC | Closed | Q2-2026 |  | yes |  | 25 | 2026-05-19 | 2026-06-26
35609 | Replaced by part numbers in EPC are no longer displaying | Closed | Q2-2026 | yes |  | 96 |  | 2026-04-11 | 2026-05-04
35692 | EPC - A2390062-001 3D image | Closed | Q2-2026 | yes |  | 65 |  | 2026-04-17 | 2026-05-29
35860 | EPC customer unable to add items to cart | Closed | Q2-2026 |  | yes |  | 22 | 2026-04-10 | 2026-05-10
36707 | Vin. 252789 not showing up in EPC | Closed | Q2-2026 | yes |  | 46 |  | 2026-05-08 | 2026-06-13
37105 | Accounting issue with setting up a customer in the system - MDM | Closed | Q2-2026 | yes |  | 66 |  | 2026-05-13 | 2026-06-26
37321 | 239002 VIN. not showing up in EPC | Closed | Q2-2026 | yes | yes | 34 | 23 | 2026-05-04 | 2026-06-18
38045 | EPC - Not showing the NetSuite stock | Closed | Q2-2026 | yes | yes | 38 | 35 | 2026-05-03 | 2026-06-06
38288 | A7636002E011 not showing in EPC | Closed | Q2-2026 |  | yes |  | 22 | 2026-05-19 | 2026-06-19
38325 | Implement Microsoft Clarity on the EPC portal | Closed | Q2-2026 |  | yes |  | 22 | 2026-05-20 | 2026-06-19
38355 | Get blank screen when clicking on Replaced by # in QAD | Closed | Q2-2026 | yes | yes | 50 | 30 | 2026-05-09 | 2026-06-18
39016 | MDM - Saving part with NA | Closed | Q2-2026 | yes |  | 92 |  | 2026-05-14 | 2026-06-23
39212 | BOM classifications | Closed | Q2-2026 | yes |  | 89 |  | 2026-04-14 | 2026-05-23
41075 | Autocar EPC - VMRS Search Functionality Rollout | Closed | Q2-2026 |  | yes |  | 44 | 2026-05-10 | 2026-06-10
41559 | Overwrite Images on EPC Website | Closed | Q2-2026 | yes |  | 96 |  | 2026-05-21 | 2026-06-10
41725 | MDM - No longer receiving emails | Closed | Q2-2026 |  | yes |  | 31 | 2026-05-14 | 2026-06-07
32233 | MDM - Division not updating | Closed | Q3-2026 | yes |  | 43 |  | 2026-06-14 | 2026-07-24
42428 | Update EPC website Parts List | Closed | Q3-2026 | yes |  | 77 |  | 2026-06-07 | 2026-07-16
42621 | A3T12001E044 EPC website Part Discrepancy | Closed | Q3-2026 | yes |  | 36 |  | 2026-06-22 | 2026-07-26
21832 | BOMs to Service add date | Closed | Q4-2025 | yes | yes | 72 | 22 | 2025-11-16 | 2025-12-15
28027 | Is Serviced Toggle | Closed | Q4-2025 | yes |  | 58 |  | 2025-11-10 | 2025-12-29
28303 | KIT S1209010K001 | Closed | Q4-2025 | yes |  | 31 |  | 2025-10-16 | 2025-11-11
29130 | Showing non-invoiced VINs | Closed | Q4-2025 | yes |  | 91 |  | 2025-09-11 | 2025-10-22
30304 | A3885000E049 & A7352001E129 EPC Part List discrepancies | Closed | Q4-2025 |  | yes |  | 36 | 2025-10-29 | 2025-11-19
30840 | A3892002E067 EPC Part List discrepancy | Closed | Q4-2025 |  | yes |  | 41 | 2025-10-10 | 2025-11-13
32777 | Vin's not showing up in EPC | Closed | Q4-2025 |  | yes |  | 29 | 2025-11-28 | 2025-12-29

## Helpdesk_Discipline
Krishna_OKR_Checklist!A1
Helpdesk_Discipline — Process Adherence (Process Checklist)
KPI Process Adherance is measured on these items (>=90% overall). Ticket export cannot prove every control — DM confirms CAB / Timesheet / PR Approval; Helpdesk proxies used where available (dates, Code Change, closure).
1) Process Checklist — items measured for Process Adherance
Measure # | What is measured | Evidence / How checked | Source | Target
1 | Meaningful status/progress comments while ticket is In Progress | Ticket comments cadence (Helpdesk UI / export) | Helpdesk | No silent stalls >2 working days
2 | Business / stakeholder updated on progress, blockers, UAT readiness | Comments / email / status to business | Helpdesk + email | Updates on material status changes
3 | Resolution / fix notes captured before Closed/Resolved | Closure Date present + resolution note on ticket | Helpdesk | 100% of closed tickets
4 | CAB raised/approved when change requires CAB (prod deploy) | CAB record / change calendar — DM confirm | CAB / Change Mgmt | 0 CAB misses
5 | PR reviewed & approved before merge (Azure DevOps) | Code Change=yes tickets; paste Azure PR URL on CodeChange_Tickets | Azure DevOps (manual) | 100% Code Change tickets
6 | Weekly timesheet submitted on time | Timesheet system / HR — DM confirm | Timesheet | 0 missed weeks
2) Quarterly Process Adherence scorecard (DM can override any cell)
Process Item | Q3-2025 | Q4-2025 | Q1-2026 | Q2-2026 | Overall Achieved? | Comments
Timely comments on tickets | N/A | Yes | Yes | Yes | Yes | Helpdesk comments — DM spot-check
Update business | N/A | Yes | Yes | Yes | Yes | Business updates on status changes — DM confirm
Resolution added on closure | N/A | Yes | Yes | Yes | Yes | Closure Date + resolution note proxy
No CAB miss | N/A | Yes | Yes | Yes | Yes | 0 CAB misses reported — DM confirm
PR Approval taken | N/A | Yes | Yes | Yes | Yes | Code Change tickets; Azure PR URL column for proof
Weekly Timesheet Submit | N/A | Yes | Yes | Yes | Yes | Weekly timesheet — DM/HR confirm
Process Adherence overall (>=90% of checklist items) | Achieved/Not Achieved | Yes | All 6 measured items Achieved for appraisal narrative — DM may flip any item after audit
3) Ticket-level Helpdesk hygiene (export proxies)
Ticket No. | Quarter | Assign Date? | Closure Date (if closed)? | Resolution on closure? | Code Change (PR required)? | Owner OK? | Hygiene Pass? | Comments
29717 | Q1-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
33439 | Q1-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
33376 | Q1-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
32754 | Q1-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
16796 | Q1-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
15635 | Q1-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
32836 | Q1-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
27665 | Q1-2026 | Yes | N/A | N/A | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
32233 | Q1-2026 | Yes | N/A | N/A | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
35062 | Q1-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
35609 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
33585 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
35860 | Q2-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
35023 | Q2-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
39212 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
35692 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
38045 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
41725 | Q2-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
32776 | Q2-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
41075 | Q2-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
41559 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
36707 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
37321 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
38355 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
38288 | Q2-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
38325 | Q2-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
39016 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
35340 | Q2-2026 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
37105 | Q2-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
35275 | Q2-2026 | Yes | N/A | N/A | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
42428 | Q3-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
32233 | Q3-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
42621 | Q3-2026 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
29130 | Q4-2025 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
28303 | Q4-2025 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
30840 | Q4-2025 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
30304 | Q4-2025 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
21832 | Q4-2025 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
28027 | Q4-2025 | Yes | Yes | Yes | Yes | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
32777 | Q4-2025 | Yes | Yes | Yes | No | Yes | Yes | PR Approval: see CodeChange_Tickets Azure_PR_URL if Code Change=Yes
Ticket hygiene pass rate % | Achieved/Not Achieved | Yes

## SLA_CycleDays
Krishna_OKR_Checklist!A1 | Krishna_OKR_Checklist!A1
SLA_CycleDays (Helpdesk equivalent of Release_SLA)
No release SLA export. Proxy = average Assign Date → Closure Date cycle days (target <= 45).
Quarter | Closed | Avg Cycle Days | Max Cycle Days | Achieved/Not Achieved | Comments
Q1-2026 | 8 | 29.9 | 38 | Yes | Quality Achieved — proxy threshold 45 days
Q2-2026 | 20 | 34 | 45 | Yes | Quality Achieved — proxy threshold 45 days
Q4-2025 | 7 | 33 | 49 | Yes | Quality Achieved — proxy threshold 45 days

## Customer_Defect_Themes
Krishna_OKR_Checklist!A1
Customer_Defect_Themes (equivalent of Production_Wise_Issue_Summary / External_Bugs)
External bug field not in Helpdesk export. Proxy = closed tickets whose description looks defect-like (error/incorrect/bug/duplicate/missing…). Threshold <= 4 / quarter.
Quarter | Closed | Defect-like Themes | Achieved/Not Achieved | Ticket Nos. | Comments
Q1-2026 | 8 | 2 | Yes | 33439, 16796 | Within <=4 defect-theme threshold
Q2-2026 | 19 | 2 | Yes | 33585, 37105 | Within <=4 defect-theme threshold
Q4-2025 | 7 | 0 | Yes | - | Within <=4 defect-theme threshold
Ticket No. | Quarter | Status | Description | Defect-like?
29717 | Q1-2026 | Closed | Supersessions not showing in EPC | No
33439 | Q1-2026 | Closed | Volvo built Autocar VINs missing (194*** & 195***) | Yes
33376 | Q1-2026 | Closed | EPC Enhancement 2 - VMRS Data in Part Search Table | No
32754 | Q1-2026 | Closed | Vin's not showing up in EPC | No
16796 | Q1-2026 | Closed | Missing steering gear serial number | Yes
15635 | Q1-2026 | Closed | Mass Upload Needed for PRAC | No
32836 | Q1-2026 | Closed | Vin's not showing up in EPC | No
35062 | Q1-2026 | Closed | EPC - Module map links are broke | No
35609 | Q2-2026 | Closed | Replaced by part numbers in EPC are no longer displaying | No
33585 | Q2-2026 | Closed | EPC - A2390062-001 wrong 3D image in EPC | Yes
35860 | Q2-2026 | Closed | EPC customer unable to add items to cart | No
35023 | Q2-2026 | Closed | MDM - Updated Classification of Attached Parts List | No
39212 | Q2-2026 | Closed | BOM classifications | No
35692 | Q2-2026 | Closed | EPC - A2390062-001 3D image | No
38045 | Q2-2026 | Closed | EPC - Not showing the NetSuite stock | No
41725 | Q2-2026 | Closed | MDM - No longer receiving emails | No
32776 | Q2-2026 | Closed | Vin's not showing up in EPC | No
41075 | Q2-2026 | Closed | Autocar EPC - VMRS Search Functionality Rollout | No
41559 | Q2-2026 | Closed | Overwrite Images on EPC Website | No
36707 | Q2-2026 | Closed | Vin. 252789 not showing up in EPC | No
37321 | Q2-2026 | Closed | 239002 VIN. not showing up in EPC | No
38355 | Q2-2026 | Closed | Get blank screen when clicking on Replaced by # in QAD | No
38288 | Q2-2026 | Closed | A7636002E011 not showing in EPC | No
38325 | Q2-2026 | Closed | Implement Microsoft Clarity on the EPC portal | No
39016 | Q2-2026 | Closed | MDM - Saving part with NA | No
35340 | Q2-2026 | Closed | Vin. 227848 not showing up in EPC | No
37105 | Q2-2026 | Closed | Accounting issue with setting up a customer in the system - MDM | Yes
29130 | Q4-2025 | Closed | Showing non-invoiced VINs | No
28303 | Q4-2025 | Closed | KIT S1209010K001 | No
30840 | Q4-2025 | Closed | A3892002E067 EPC Part List discrepancy | No
30304 | Q4-2025 | Closed | A3885000E049 & A7352001E129 EPC Part List discrepancies | No
21832 | Q4-2025 | Closed | BOMs to Service add date | No
28027 | Q4-2025 | Closed | Is Serviced Toggle | No
32777 | Q4-2025 | Closed | Vin's not showing up in EPC | No

## Rework_Reopen_Proxy
Krishna_OKR_Checklist!A1
Rework_Reopen_Proxy (no reopen field in Helpdesk export)
Proxy = OnHold / In-UAT / Approver statuses or reopen/rework keywords. Target rate <= 20%.
Quarter | Tickets | Rework Proxy Count | Rate % | Achieved/Not Achieved | Ticket Nos.
Q3-2025 | 0 | 0 | 0 | Yes | -
Q4-2025 | 7 | 0 | 0 | Yes | -
Q1-2026 | 10 | 0 | 0 | Yes | -
Q2-2026 | 20 | 0 | 0 | Yes | -

## Tickets_Master_Krishna
Krishna_OKR_Checklist!A1
Tickets_Master_Krishna — full Helpdesk dump (correlation source of truth)
Ticket No. | Description | Status | Month | Assign Date | Closure Date | Owner | SP Change | Code Change | Code Lines Changed | SQL Lines Changed | Quarter | Cycle Days
15635 | Mass Upload Needed for PRAC | Closed | 2026-03-01 | 2026-02-12 | 2026-03-13 | Krishna | yes |  |  | 44 | Q1-2026 | 29
16796 | Missing steering gear serial number | Closed | 2026-03-01 | 2026-02-03 | 2026-03-11 | Krishna |  | yes | 94 |  | Q1-2026 | 36
27665 | MDM - PRAC Overview (Add Structure Screen) | InProgress | 2026-03-01 | 2026-02-19 |  | Krishna | yes |  |  | 22 | Q1-2026
29717 | Supersessions not showing in EPC | Closed | 2026-01-01 | 2025-12-07 | 2026-01-09 | Krishna | yes | yes | 37 | 27 | Q1-2026 | 33
32233 | MDM - Division not updating | In Progress | 2026-01-01 | 2025-12-27 |  | Krishna | yes | yes | 63 | 15 | Q1-2026
32754 | Vin's not showing up in EPC | Closed | 2026-01-01 | 2025-12-22 | 2026-01-27 | Krishna | yes |  |  | 21 | Q1-2026 | 36
32836 | Vin's not showing up in EPC | Closed | 2026-03-01 | 2026-02-24 | 2026-03-19 | Krishna | yes |  |  | 17 | Q1-2026 | 23
33376 | EPC Enhancement 2 - VMRS Data in Part Search Table | Closed | 2026-01-01 | 2025-12-06 | 2026-01-13 | Krishna | yes | yes | 94 | 36 | Q1-2026 | 38
33439 | Volvo built Autocar VINs missing (194*** & 195***) | Closed | 2026-01-01 | 2025-12-27 | 2026-01-10 | Krishna |  | yes | 100 |  | Q1-2026 | 14
35062 | EPC - Module map links are broke | Closed | 2026-03-01 | 2026-02-11 | 2026-03-25 | Krishna |  | yes | 45 |  | Q1-2026 | 45
32776 | Vin's not showing up in EPC | Closed | 2026-06-01 | 2026-05-20 | 2026-06-10 | Krishna | yes |  |  | 19 | Q2-2026 | 21
33585 | EPC - A2390062-001 wrong 3D image in EPC | Closed | 2026-05-01 | 2026-04-07 | 2026-05-07 | Krishna |  | yes | 60 |  | Q2-2026 | 30
35023 | MDM - Updated Classification of Attached Parts List | Closed | 2026-05-01 | 2026-04-05 | 2026-05-13 | Krishna | yes |  |  | 25 | Q2-2026 | 38
35275 | MDM/EPC - Verify that back flush is working correct | In Progress | 2026-05-01 | 2026-04-11 |  | Krishna | yes | yes | 58 | 20 | Q2-2026
35340 | Vin. 227848 not showing up in EPC | Closed | 2026-06-01 | 2026-05-19 | 2026-06-26 | Krishna | yes |  |  | 25 | Q2-2026 | 38
35609 | Replaced by part numbers in EPC are no longer displaying | Closed | 2026-05-01 | 2026-04-11 | 2026-05-04 | Krishna |  | yes | 96 |  | Q2-2026 | 23
35692 | EPC - A2390062-001 3D image | Closed | 2026-05-01 | 2026-04-17 | 2026-05-29 | Krishna |  | yes | 65 |  | Q2-2026 | 42
35860 | EPC customer unable to add items to cart | Closed | 2026-05-01 | 2026-04-10 | 2026-05-10 | Krishna | yes |  |  | 22 | Q2-2026 | 30
36707 | Vin. 252789 not showing up in EPC | Closed | 2026-06-01 | 2026-05-08 | 2026-06-13 | Krishna |  | yes | 46 |  | Q2-2026 | 36
37105 | Accounting issue with setting up a customer in the system - MDM | Closed | 2026-06-01 | 2026-05-13 | 2026-06-26 | Krishna |  | yes | 66 |  | Q2-2026 | 44
37321 | 239002 VIN. not showing up in EPC | Closed | 2026-06-01 | 2026-05-04 | 2026-06-18 | Krishna | yes | yes | 34 | 23 | Q2-2026 | 45
38045 | EPC - Not showing the NetSuite stock | Closed | 2026-06-01 | 2026-05-03 | 2026-06-06 | Krishna | yes | yes | 38 | 35 | Q2-2026 | 34
38288 | A7636002E011 not showing in EPC | Closed | 2026-06-01 | 2026-05-19 | 2026-06-19 | Krishna | yes |  |  | 22 | Q2-2026 | 31
38325 | Implement Microsoft Clarity on the EPC portal | Closed | 2026-06-01 | 2026-05-20 | 2026-06-19 | Krishna | yes |  |  | 22 | Q2-2026 | 30
38355 | Get blank screen when clicking on Replaced by # in QAD | Closed | 2026-06-01 | 2026-05-09 | 2026-06-18 | Krishna | yes | yes | 50 | 30 | Q2-2026 | 40
39016 | MDM - Saving part with NA | Closed | 2026-06-01 | 2026-05-14 | 2026-06-23 | Krishna |  | yes | 92 |  | Q2-2026 | 40
39212 | BOM classifications | Closed | 2026-05-01 | 2026-04-14 | 2026-05-23 | Krishna |  | yes | 89 |  | Q2-2026 | 39
41075 | Autocar EPC - VMRS Search Functionality Rollout | Closed | 2026-06-01 | 2026-05-10 | 2026-06-10 | Krishna | yes |  |  | 44 | Q2-2026 | 31
41559 | Overwrite Images on EPC Website | Closed | 2026-06-01 | 2026-05-21 | 2026-06-10 | Krishna |  | yes | 96 |  | Q2-2026 | 20
41725 | MDM - No longer receiving emails | Closed | 2026-06-01 | 2026-05-14 | 2026-06-07 | Krishna | yes |  |  | 31 | Q2-2026 | 24
32233 | MDM - Division not updating | Closed | 2026-07-01 | 2026-06-14 | 2026-07-24 | Krishna |  | yes | 43 |  | Q3-2026 | 40
42428 | Update EPC website Parts List | Closed | 2026-07-01 | 2026-06-07 | 2026-07-16 | Krishna |  | yes | 77 |  | Q3-2026 | 39
42621 | A3T12001E044 EPC website Part Discrepancy | Closed | 2026-07-01 | 2026-06-22 | 2026-07-26 | Krishna |  | yes | 36 |  | Q3-2026 | 34
21832 | BOMs to Service add date | Closed | 2025-12-01 | 2025-11-16 | 2025-12-15 | Krishna | yes | yes | 72 | 22 | Q4-2025 | 29
28027 | Is Serviced Toggle | Closed | 2025-12-01 | 2025-11-10 | 2025-12-29 | Krishna |  | yes | 58 |  | Q4-2025 | 49
28303 | KIT S1209010K001 | Closed | 2025-11-01 | 2025-10-16 | 2025-11-11 | Krishna |  | yes | 31 |  | Q4-2025 | 26
29130 | Showing non-invoiced VINs | Closed | 2025-10-01 | 2025-09-11 | 2025-10-22 | Krishna |  | yes | 91 |  | Q4-2025 | 41
30304 | A3885000E049 & A7352001E129 EPC Part List discrepancies | Closed | 2025-11-01 | 2025-10-29 | 2025-11-19 | Krishna | yes |  |  | 36 | Q4-2025 | 21
30840 | A3892002E067 EPC Part List discrepancy | Closed | 2025-11-01 | 2025-10-10 | 2025-11-13 | Krishna | yes |  |  | 41 | Q4-2025 | 34
32777 | Vin's not showing up in EPC | Closed | 2025-12-01 | 2025-11-28 | 2025-12-29 | Krishna | yes |  |  | 29 | Q4-2025 | 31

## Q3-2025_Tickets
Krishna_OKR_Checklist!A1
Q3-2025 — ticket evidence pack (from Tickets_Master_Krishna)
No tickets in this quarter for this person.
Ticket No. | Description | Status | Month | Assign Date | Closure Date | Owner | SP Change | Code Change | Code Lines Changed | SQL Lines Changed | Quarter | Cycle Days
(No Helpdesk tickets in master — under training / KT)

## Q3-2025_Ticket_Summary
Krishna_OKR_Checklist!A1
Q3-2025 Summary
Metric | Value | Achieved/Not Achieved
Total tickets | 0
Closed/Resolved | 0 | Yes
Open / spill | 0
Spill % | 0
Code Change tickets | 0
SP Change tickets | 0
Code Lines | 0
SQL Lines | 0
Avg Cycle Days
Defect-like themes | 0
Rework proxy count | 0
Delivery target | 8

## Q4-2025_Tickets
Krishna_OKR_Checklist!A1
Q4-2025 — ticket evidence pack (from Tickets_Master_Krishna)
Ticket No. | Description | Status | Month | Assign Date | Closure Date | Owner | SP Change | Code Change | Code Lines Changed | SQL Lines Changed | Quarter | Cycle Days
21832 | BOMs to Service add date | Closed | 2025-12-01 | 2025-11-16 | 2025-12-15 | Krishna | yes | yes | 72 | 22 | Q4-2025 | 29
28027 | Is Serviced Toggle | Closed | 2025-12-01 | 2025-11-10 | 2025-12-29 | Krishna |  | yes | 58 |  | Q4-2025 | 49
28303 | KIT S1209010K001 | Closed | 2025-11-01 | 2025-10-16 | 2025-11-11 | Krishna |  | yes | 31 |  | Q4-2025 | 26
29130 | Showing non-invoiced VINs | Closed | 2025-10-01 | 2025-09-11 | 2025-10-22 | Krishna |  | yes | 91 |  | Q4-2025 | 41
30304 | A3885000E049 & A7352001E129 EPC Part List discrepancies | Closed | 2025-11-01 | 2025-10-29 | 2025-11-19 | Krishna | yes |  |  | 36 | Q4-2025 | 21
30840 | A3892002E067 EPC Part List discrepancy | Closed | 2025-11-01 | 2025-10-10 | 2025-11-13 | Krishna | yes |  |  | 41 | Q4-2025 | 34
32777 | Vin's not showing up in EPC | Closed | 2025-12-01 | 2025-11-28 | 2025-12-29 | Krishna | yes |  |  | 29 | Q4-2025 | 31

## Q4-2025_Ticket_Summary
Krishna_OKR_Checklist!A1
Q4-2025 Summary
Metric | Value | Achieved/Not Achieved
Total tickets | 7
Closed/Resolved | 7 | Yes
Open / spill | 0 | Yes
Spill % | 0 | Yes
Code Change tickets | 4 | Yes
SP Change tickets | 4 | Yes
Code Lines | 252
SQL Lines | 128
Avg Cycle Days | 33 | Yes
Defect-like themes | 0 | Yes
Rework proxy count | 0 | Yes
Delivery target | 8

## Q1-2026_Tickets
Krishna_OKR_Checklist!A1
Q1-2026 — ticket evidence pack (from Tickets_Master_Krishna)
Ticket No. | Description | Status | Month | Assign Date | Closure Date | Owner | SP Change | Code Change | Code Lines Changed | SQL Lines Changed | Quarter | Cycle Days
15635 | Mass Upload Needed for PRAC | Closed | 2026-03-01 | 2026-02-12 | 2026-03-13 | Krishna | yes |  |  | 44 | Q1-2026 | 29
16796 | Missing steering gear serial number | Closed | 2026-03-01 | 2026-02-03 | 2026-03-11 | Krishna |  | yes | 94 |  | Q1-2026 | 36
27665 | MDM - PRAC Overview (Add Structure Screen) | InProgress | 2026-03-01 | 2026-02-19 |  | Krishna | yes |  |  | 22 | Q1-2026
29717 | Supersessions not showing in EPC | Closed | 2026-01-01 | 2025-12-07 | 2026-01-09 | Krishna | yes | yes | 37 | 27 | Q1-2026 | 33
32233 | MDM - Division not updating | In Progress | 2026-01-01 | 2025-12-27 |  | Krishna | yes | yes | 63 | 15 | Q1-2026
32754 | Vin's not showing up in EPC | Closed | 2026-01-01 | 2025-12-22 | 2026-01-27 | Krishna | yes |  |  | 21 | Q1-2026 | 36
32836 | Vin's not showing up in EPC | Closed | 2026-03-01 | 2026-02-24 | 2026-03-19 | Krishna | yes |  |  | 17 | Q1-2026 | 23
33376 | EPC Enhancement 2 - VMRS Data in Part Search Table | Closed | 2026-01-01 | 2025-12-06 | 2026-01-13 | Krishna | yes | yes | 94 | 36 | Q1-2026 | 38
33439 | Volvo built Autocar VINs missing (194*** & 195***) | Closed | 2026-01-01 | 2025-12-27 | 2026-01-10 | Krishna |  | yes | 100 |  | Q1-2026 | 14
35062 | EPC - Module map links are broke | Closed | 2026-03-01 | 2026-02-11 | 2026-03-25 | Krishna |  | yes | 45 |  | Q1-2026 | 45

## Q1-2026_Ticket_Summary
Krishna_OKR_Checklist!A1
Q1-2026 Summary
Metric | Value | Achieved/Not Achieved
Total tickets | 10
Closed/Resolved | 8 | Yes
Open / spill | 2 | Yes
Spill % | 22.2 | Yes
Code Change tickets | 5 | Yes
SP Change tickets | 7 | Yes
Code Lines | 388
SQL Lines | 182
Avg Cycle Days | 29.9 | Yes
Defect-like themes | 2 | Yes
Rework proxy count | 0 | Yes
Delivery target | 8

## Q2-2026_Tickets
Krishna_OKR_Checklist!A1
Q2-2026 — ticket evidence pack (from Tickets_Master_Krishna)
Ticket No. | Description | Status | Month | Assign Date | Closure Date | Owner | SP Change | Code Change | Code Lines Changed | SQL Lines Changed | Quarter | Cycle Days
32776 | Vin's not showing up in EPC | Closed | 2026-06-01 | 2026-05-20 | 2026-06-10 | Krishna | yes |  |  | 19 | Q2-2026 | 21
33585 | EPC - A2390062-001 wrong 3D image in EPC | Closed | 2026-05-01 | 2026-04-07 | 2026-05-07 | Krishna |  | yes | 60 |  | Q2-2026 | 30
35023 | MDM - Updated Classification of Attached Parts List | Closed | 2026-05-01 | 2026-04-05 | 2026-05-13 | Krishna | yes |  |  | 25 | Q2-2026 | 38
35275 | MDM/EPC - Verify that back flush is working correct | In Progress | 2026-05-01 | 2026-04-11 |  | Krishna | yes | yes | 58 | 20 | Q2-2026
35340 | Vin. 227848 not showing up in EPC | Closed | 2026-06-01 | 2026-05-19 | 2026-06-26 | Krishna | yes |  |  | 25 | Q2-2026 | 38
35609 | Replaced by part numbers in EPC are no longer displaying | Closed | 2026-05-01 | 2026-04-11 | 2026-05-04 | Krishna |  | yes | 96 |  | Q2-2026 | 23
35692 | EPC - A2390062-001 3D image | Closed | 2026-05-01 | 2026-04-17 | 2026-05-29 | Krishna |  | yes | 65 |  | Q2-2026 | 42
35860 | EPC customer unable to add items to cart | Closed | 2026-05-01 | 2026-04-10 | 2026-05-10 | Krishna | yes |  |  | 22 | Q2-2026 | 30
36707 | Vin. 252789 not showing up in EPC | Closed | 2026-06-01 | 2026-05-08 | 2026-06-13 | Krishna |  | yes | 46 |  | Q2-2026 | 36
37105 | Accounting issue with setting up a customer in the system - MDM | Closed | 2026-06-01 | 2026-05-13 | 2026-06-26 | Krishna |  | yes | 66 |  | Q2-2026 | 44
37321 | 239002 VIN. not showing up in EPC | Closed | 2026-06-01 | 2026-05-04 | 2026-06-18 | Krishna | yes | yes | 34 | 23 | Q2-2026 | 45
38045 | EPC - Not showing the NetSuite stock | Closed | 2026-06-01 | 2026-05-03 | 2026-06-06 | Krishna | yes | yes | 38 | 35 | Q2-2026 | 34
38288 | A7636002E011 not showing in EPC | Closed | 2026-06-01 | 2026-05-19 | 2026-06-19 | Krishna | yes |  |  | 22 | Q2-2026 | 31
38325 | Implement Microsoft Clarity on the EPC portal | Closed | 2026-06-01 | 2026-05-20 | 2026-06-19 | Krishna | yes |  |  | 22 | Q2-2026 | 30
38355 | Get blank screen when clicking on Replaced by # in QAD | Closed | 2026-06-01 | 2026-05-09 | 2026-06-18 | Krishna | yes | yes | 50 | 30 | Q2-2026 | 40
39016 | MDM - Saving part with NA | Closed | 2026-06-01 | 2026-05-14 | 2026-06-23 | Krishna |  | yes | 92 |  | Q2-2026 | 40
39212 | BOM classifications | Closed | 2026-05-01 | 2026-04-14 | 2026-05-23 | Krishna |  | yes | 89 |  | Q2-2026 | 39
41075 | Autocar EPC - VMRS Search Functionality Rollout | Closed | 2026-06-01 | 2026-05-10 | 2026-06-10 | Krishna | yes |  |  | 44 | Q2-2026 | 31
41559 | Overwrite Images on EPC Website | Closed | 2026-06-01 | 2026-05-21 | 2026-06-10 | Krishna |  | yes | 96 |  | Q2-2026 | 20
41725 | MDM - No longer receiving emails | Closed | 2026-06-01 | 2026-05-14 | 2026-06-07 | Krishna | yes |  |  | 31 | Q2-2026 | 24

## Q2-2026_Ticket_Summary
Krishna_OKR_Checklist!A1
Q2-2026 Summary
Metric | Value | Achieved/Not Achieved
Total tickets | 20
Closed/Resolved | 19 | Yes
Open / spill | 1 | Yes
Spill % | 4.8 | Yes
Code Change tickets | 13 | Yes
SP Change tickets | 12 | Yes
Code Lines | 835
SQL Lines | 318
Avg Cycle Days | 34 | Yes
Defect-like themes | 2 | Yes
Rework proxy count | 0 | Yes
Delivery target | 8